## Sprint Sheet
Story Count | Story | Assigned | Delivery Date | Module | Details | Lable | Status | UAT Comment/ Deployment Platforms | QA Comment | Retesting
Sprint Plan for 19-12-2023 to 03-01-2023
1 | Kanban board | Priya / Ravi | 2023-03-01 | Timesheet | Drag & Drop facility with status change automatically) | P-1 | Done |  | Tested | Re-Tested
2 | Add Employee with option of add others task , approved task | Priya / Ravi | 2023-03-01 | Timesheet | Provide facility to manager that he can give power to his sub ordinate in his absence selected subordinate can create task for team , approve task or delete task also in a check box | P-1 | Done |  | Tested | Re-Tested
3 | Mail integration when we assign a task to user | Priya / Ravi | 2023-03-01 | Timesheet | When task created , and closed or send for approval | P-1 | Done |  | Tested | Re-Tested
4 | Multiple Comment with attachment | Priya / Ravi | 2023-03-01 | Timesheet | Discussion or chat window | P-1 | Done |  | Tested | Re-Tested
5 | All Employee List Not Visible in add Resource | Priya / Ravi | 2023-03-01 | Timesheet | Completed | P-1 | Done |  | Tested | Re-Tested
6 | Multiple Attachment Highlighted blue link | Priya / Ravi | 2023-03-01 | Timesheet | Link will be clickable and view attached file when user click on it | P-1 | Done |  | Tested | Re-Tested
7 | Remove Extra Comment | Priya / Ravi | 2023-03-01 | Timesheet | Completed | P-1 | Done |  | Himanshu Tested | Re-Tested
8 | employee can see only his task on dashboard and project task but PM can view all task of his team on both dashboard and project task | Priya / Ravi | 2023-03-01 | Timesheet | When developer or Employee login to project he only able to view his task but manager can view all is employees task | P-1 | Done |  | Tested | Re-Tested
9 | Modified Dashboard | Priya / Ravi | 2023-03-01 | Timesheet | Ashwin ji provided that dashboard | P-1 | Done |  | Tested | Re-Tested
10 | Excel type (Jira, Azure, Emossy) | Priya / Ravi | 44986 | Timesheet | Azure , Jira and Emossy selection in Import excel option in drop down | P-1 | Done |  | Not Tested | Didn't had the exported file of task to upload
11 | On click of dashboard task rout on project task | Priya / Ravi | 2023-03-01 | Timesheet | All dashboard content will rout to task sheet and filtered result as per dashboard option | P-1 | Done |  | Tested | Re-Tested
12 | Admin can view all org project and create task also | Priya / Ravi | 2023-03-01 | Timesheet | Admin can view all project of organization also create task but delete and approval of task will not available | P-1 | Spillover |  | Fail | Failed Admin is unable to create the task as the admin is not in the team of project still the admin also need permission to create tasks | Spillover to next sprint
13 | Pay roll Run with tax calculation | Harshit / Bhaven | 2023-03-01 | Payroll | Run payroll on live with calculation | P-1 | Done |  | Not Tested | Under Testing on UAT
14 | Performance New | Deepali / Mayank | 2023-03-01 | Performance | Run Performance n Live with all Sub-Modules | P-1 | Done |  | Tested | Re-Tested
15 | User access Dev- Deployment | Shagun / Ankit | 2023-03-01 | User Access | User Access Permission Dev Deploye | P-1 | Done | Pending | Under Testing | Under Testing
16 | EFMS (Employee Feedback management system ) | Deepali / Mayank | 2023-03-01 | EFMS | Approved, Rejected,Deleted, Delete Request , and all Status Change Then Send Mail Live, Goal Management | P-1 | Done |  | Tested | Under Testing
17 | Company Logo | Bhaven | 2023-03-01 | Login page | Company Logo Remove from Moreyeahs Live | P-1 | Done |  | Himanshu Tested | Re-Tested
18 | Bug resolve | Team | 2023-03-01 | Bug | 401 Error Resolve ,Client Requierment Changes ,Hiring Dashboard ,Company Created Mail Send Resolve Live, Attendence Dashboard remove | P-1 | Done |  | Tested | Re-Tested On Attendance dashboard there is still static data on UAT
19 | Client Issues Fix | Team | 2023-03-01 | Client | Org Creation Fix , Edit employee bug, Employee directory issue , Admin profile routing Fix | P-2 | Done |  | Tested | Under Testing
20 | Delete project manager | Bhaven | 2023-03-01 | Project | Without Adding new PM into project old PM will not remove from project | P-1 | Done |  | Tested | Re-Tested
21 | Whole Week or Month Task (Recurring Task) | Priya / Ravi | 2023-03-01 | Timesheet | If manager create task for his employees for a month or 2 week then same task will be carry forware in next week time sheet and add time in his total log time | P-1 | Done |  | Tested | Re-Tested
22 | Multiple projects created from single task page | Priya / Ravi | 2023-03-01 | Timesheet | User can create task of multiple project from single task form | P-2 | Done |  | Tested | Re-Tested
Regression Sprint Plan After 03-01-2023 to
23 | Timesheet Bugs fix | Priya / Ravi / Shagun / Bhavendr | 2023-11-01 | Timesheet | Time Sheet Bug Fixes which are provided by Tester and others PM's | P-1 | Done |  | Tested | Re-Tested
24 | Reminder mail facility for Incomplete timesheet | Ravi / Ankit / Harshit | 2023-11-01 | Timesheet | Send a reminder mail for those people in project who are not inputting time in a task | P-1 | Done |  | Tested
25 | Org Tree Fix | Bhavendr / Harshit | 2023-11-01 | Org Tree | Org Tree is not working properly so, manage fixes and change in code | P-1 | Done |  | Under Testing
26 | Client Requirement of To-Do List | Suraj / Pradanya | 2023-11-01 | To-Do | According to client requirement a new module integrated in Emossy to-do where a user can manage its daily to-do sheet at the dashboard | P-1 | Done |  | Tested
27 | Client Requirement of Attendance Dashboard Fix | Bhavendr / Harshit | 2023-11-01 | Attendance Module | Attendance dashboard is not working properly fix the bug now working properly | P-1 | Done |  | Under Testing
28 | Hiring Issue Fixes | Shagun / Ankit | 2023-11-01 | Hiring Module | Change Flow Request And Bugs Fixes In Hiring provided by HR's | P-1 | Done |  | Tested
Date Of Last Deployment - 11, Jan 2023 to 25-jan-2023
32 | Project also can closed / Hold | Suraj / Pradanya |  | Project | The project also can closed with a Mandatory document upload like signoff doc. | P-1 | Pending
33 | Server maintenance page at the time of Live deployment | Deepali / Harshit |  | deployment | Create a page for we are under maintenance and will be show at the time of live deployment process | P-1 | Pending
34 | Microsoft login issue | Harshit / Bhaven |  | Login page | In morning Microsoft loing not working showing DNS error | P-2 | Pending
35 | Client Branch for Urgent Fixes | Harshit / Bhaven |  | deployment | Create a New Client Name branch for quick Resolving issues or meet client requirement | P-1 | Done
36 | Org chart not working | Harshit / Bhaven |  | Me | Org Chart view with unassigned reporting manager | P-2 | Done |  | Tested
38 | Add custom date filter in the task board | Priya / Ravi |  | Timesheet | For Report or find any custome date working hours | P-2 | Pending
39 | Task Status on Timesheet page , Pending, close , In- progress | Priya / Ravi |  | Timesheet | Will be help in finding task which are approved or not | P-1 | Pending
42 | Backlog Task created / User story | Priya / Ravi |  | Timesheet | Only with title information backlog task will created | P-1 | Done |  | Tested
43 | Admin can view all org project and create task also | Priya / Ravi |  | Timesheet | Admin can view all project of organization also create task but delete and approval of task will not available | P-1 | Pending
44 | ISA app for mobile | Faizan |  | Mobile App | Client App for ISA | P-1 | Pending
45 | Todo at home Page | Suraj / Pradanya |  | Home Page | Create Todo Task for reminder | P-1 | Done |  | Tested
50 | User access Permission | Shagun / Ankit |  | User Access | Live Deployment of User Access | P-2 | Pending
55 | Mention Functionality on Home page Post & Announcement | Harshit / Bhaven |  | Home Page | All Mail id at select at one mail | P-2 | Pending
Regression Sprint Plan After 25, Jan 2023 Live Deployment Till 2, Feb 2023
Bug Id | Details | Module Name | Bug On | Completed By | Reported By | Status | Complete Date | QA Status | Live Comment
#021 | Attendance Report (Client Demand) | Attendance | Back end / Front end | Harshit Mitra / Bhavendr Singh Jat | Kovid Parekh | DONE | 29, Jan 2023 | Tested and Delivered same day by Harshit sir
#025 | Multiple check-in & check-out with both Web and Mobile App | Attendance | Back end / Front end | Harshit Mitra / Bhavendr Singh Jat | Himanshu Sir |  |  | not tested
#004 | Profile image is changing on refreshment and click on profile image page should be open. | Employee Directory | Front end | Harshit Mitra / Bhavendr Singh Jat | Shounak Sir |  |  | Tested Working
#014 | On Global search name show in white color and background also in white color | Employee Directory | Front end | Priya |  | DONE |  | Tested Working
#006 | Update post is not working and delete is not proper working. | Home Wall | Front end | Pradnya/Suraj | Shagun Sir | Done |  | Tested Working
#023 | Comment and Post Sections not working as per requirement | Home Wall | Front end | Pradnya/Suraj | Himanshu Sir | Done |  | Tested Not working its allowing empty Comment with one space to submit as comment
#001 | Ticket Order By Last Update Date - This Feature is not required removed this feature | Ticket | Back end | Harshit Mitra | Hemant Sir | DONE | 27, Jan 2023 | Tested Working
#002 | Change In Task Project Board Total Spent Time Is Wrong | Time Sheet | Back end | Harshit Mitra | Manish Sir | DONE | 27, Jan 2023 | Tested Working
#003 | In My Time Sheet After Importing Task Spent Time Is Not Showing | Time Sheet | Back end | Harshit Mitra | Himanshu Sir | DONE | 27, Jan 2023 | Tested Working
#008 | Create task popup open on refresh when we come from main dashbored | Time Sheet | Front end | Priya | Himanshu Sir | DONE |  | It will be open untill it will be closed by the user, If the user wants to create multiple tasks from single pop up.
#009 | Date filter work on only first page | Time Sheet | Front end | Priya | Himanshu Sir | DONE |  | Tested Working
#010 | Back Log Pagination not working | Time Sheet | Front end | Priya | Himanshu Sir | DONE |  | Bug 1389 Bug Created Not Working
#011 | Old on leave task transfer in backlog | Time Sheet | Back end | Ravi Vyas | Himanshu Sir | DONE |  | Tested Working
#012 | backlog edit popup open in side drawer | Time Sheet | Front end | Priya | Himanshu Sir | DONE |  | Tested Working
#013 | BackLog edit popup cross button not working | Time Sheet | Front end | priya | Himanshu Sir | DONE |  | Tested Working
#015 | email for not assign task not working | Time Sheet | Backend | Ravi Vyas | Himanshu Sir | DONE |  | Tested Working
#016 | employee not remove from the project still showing in report | Time Sheet | Backend | Ravi Vyas | Himanshu Sir | DONE |  | Tested Working
#017 | blank sheet not download on send reminder | Time Sheet |  | Ravi Vyas/Priya | Himanshu Sir | DONE |  | Yet to Test in UAT
#018 | email not delevering for no task in project against employee | Time Sheet | Backend | Ravi Vyas | Himanshu Sir | DONE |  | Tested Working
#019 | Email notification setting in project | Time Sheet | Backend | Ravi Vyas/Priya | Himanshu Sir | DONE |  | Tested Working
#020 | Issue Istatistics data on dashboared not working | Time Sheet | Backend | Ravi Vyas | Himanshu Sir | DONE |  | Tested Working
#022 | Attachment not remove from Task from also image getting out of page | Time Sheet | Front end | Priya | Himanshu Sir | DONE |  | Bug Created Bug 1395
#024 | Project Dashboard for Admin with AK sir all Requirement with reports | Time Sheet | Backend/Frontend | Priya/Ravi Vyas | Himanshu Sir | DONE |  | Under Devlopment
#026 | Timesheet page top row need to be fix & total estimate time is not showing | Time Sheet | Backend/Frontend | Priya/Ravi Vyas | Himanshu Sir | dONE |  | Not Fixed
#027 | Estimated time and Spent time on task board is going out of page | Time Sheet | Front end | Priya | Himanshu Sir | DONE |  | Tested Working
#028 | Show created task ID on toaster | Time Sheet | Front end | Priya/Ravi Vyas | Himanshu Sir | DONE |  | Tested Working
#029 | The percentage calculation is not working on a project dashboard at Issues Statistics tab | Time Sheet | Backend | Ravi Vyas | Himanshu Sir | DONE |  | Tested Working
#030 | When we go to back dates and save working hours then page will be send to current week user have to go back again for last week | Time Sheet | Backend/Frontend | Priya/Ravi Vyas | Himanshu Sir | DONE |  | Tested Working
#032 | Not Routing properly after view task from project board | Time Sheet | Backend/Frontend | Priya/Ravi Vyas | Himanshu Sir | DONE |  | Tested Working
#031 | To-do Changes | Todo | Backend/Frontend | Pradnya/Suraj | AK Sir | DONE |  | Tested Working
#005 | In User Access Role Update API Case Is Not Working Make Changes In APIs | User Access | Back end | Harshit Mitra | Shounak Sir | DONE | 27, Jan 2023 | Tested Working
#007 | Implementation Get All Role and Employee By Role Id Api in Search String. | User Access | Back end | Ankit Jain | Shagun Sir | DONE | 27,jan 2023 | Tested Working
#033 | Add Calender Fillter on Timesheet | Time Sheet | Backend/Frontend | Priya/Ravi Vyas | Himanshu Sir | DONE | 27,jan 2024 | Tested Working
#034 | Exit Employee | Employee Directory | Front end/Backend | Pradnya/Suraj | Himanshu Sir | DONE |  | Not deployed Not Tested
#035 | Profile-> user middel name not updating and on Add Employee | Employee Directory | Back end | Suraj | Himanshu Sir | Done |  | Tested Working
#36 | ISA Mobile App | ISA | Flutter/BAckEnd/FrontEnd | MayankPrajapati/Faizan Khan | Ajay Sir | Done | 2,FEb 2023
Sprint Plan for 06-02-2023 to 21-02-2023
1 | one task assign to multiple employee | Priya/Ravi | 21-02-2023 | Time Sheet | Stepwise completed with add hrs | P-2
2 | Repo Link Attachment | Priya/Ravi | 21-02-2023 | Time Sheet | 3 Type (Frontend, Backend, Others) | P-1
3 | Code Reviewer Add | Priya/Ravi | 21-02-2023 | Time Sheet | Multiple People (Angular, dot net, #C Others) | P-1
4 | Document upload Tab with Description Last Save date | Priya/Ravi | 21-02-2023 | Time Sheet | Document name , type, Dynamic (SOW, BRD,PRD, Flow Chart, Others) | P-1
5 | Reports from Timesheet with admin dashboard | Harshit/Bhawen | 21-02-2023 | Project | Different type of reports will be generated from timesheet Active and non active user | P-1
6 | Project dashboard | Harshit/Bhawen | 21-02-2023 | Project | Project dashboard for admin with time sheet details who are not filling time sheet | P-1
7 | Add user stories (parent child flow) | Priya/Ravi | 21-02-2023 | Time Sheet | Task will be create under user stories in a parent and child flow | P-3
8 | Project Report for Admin | Harshit/Bhawen | 21-02-2023 | Project | Admin can view who fills time sheet and who not of all organization project with report | P-1
9 | Manage History delete task | Priya/Ravi | 21-02-2023 | Time Sheet | manage history of all deleted task | P-1
10 | Project under Sub Project | Priya/Ravi | 21-02-2023 | Time Sheet | Sub- project also create under main project like PMS | P-3
11 | Client New Requirement | Suraj/Pradanya | 21-02-2023 | Rediant/Blumintra/Nitin Sir | All New requirement and Bugs reported by client | P-1
12 | Leave , Holiday, Flexi Pay , Payroll work | Harshit/Bhawen | 21-02-2023 | Payroll | Complete the payroll including all these in this month | P-1
13 | Goal new | Ankit/ Deepali | 21-02-2023 | Goal | New goal of indisual, Department with history manage and Dashboard | P-1
14 | ISA App with all Pending work | Mayank | 21-02-2023 | ISA App | Complete the remain work as per requirement of both APP without FAil | P-1
15 | Project Fiance | Mayank | 21-02-2023 | Project | Complete the remain work as per requirement of both APP without FAil | P-1
16 | Emossy App / ISA app working | Faizan | 21-02-2023 | Emossy | Complete the remain work as per requirement of both APP without FAil | P-1
17 | End to End Testing of Emossy with proper test case of each module | Shounak/Manish | 21-02-2023 | Emossy/Mobile App | Testing with resolving history and also complete the user test case with proper document | P-1
18 | Recuritment Dashboard and complete UI Fix | Shagun | 21-02-2023 | Hiring | Recuritment dashboard and fix all Bugs | P-1
19 | Ticket Management Fix all remain work | Shagun | 21-02-2023 | Ticket | Ticket incomplete work and fix all Bugs with UI fix | P-1
Bugs Emossy Need to Fix at same time of working on above modules
Note on F11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Shounak Rampal create new project for testing

## Deployement Details of last Spr
11-01-2023 to 25-01-2023 Sprint Details
Sr.No | Story | Details | Status | UAT Comment | QA Status | Send for regression sprint
1 | User Access Permission | Permission of Emossy Module by roles | Deliverd | Working on UAT | Tested | yes
2 | Time Sheet New Requirment and Fixes | Backlog Task in project | Deliverd | Working on UAT | Tested | No
|  | Project wise report for not maintaining task , not filling time sheet | Deliverd | Working on UAT | Tested | No
|  | Single Mail notification of multiple task | Deliverd | Working on UAT | Tested | No
|  | Mail to those who are not maintaining task on time sheet | Deliverd | Working on UAt | Tested | No
|  | Task Creation is easy from the main project board, task Board , | Deliverd | Working on UAT | Tested | No
|  | Time sheet lock at once submitted for aaproval | Deliverd | Working on UAT | Tested | No
|  | Edit of task | Deliverd | Editing functionality is working but its making te estimate time 0 | Tested | yes
|  | Task Status on Timesheet page , Pending, close , In- progress | Deliverd | Working on UAT | Tested | No
|  | Report on approved task tab | Deliverd | Working but customization required | Tested | No
|  | Cheq team jira excel upload for multiple task | Deliverd | Working on UAT | Tested | No
3 | Project also can closed / Hold | We can also change status of project by upload document | Deliverd | Working on UAT need more modifications its should not allow Resources to create task | Tested | No
4 | Server maintenance page at the time of Live deployment | When we are going for Live or prod. the page will be activated | Deliverd | Working on UAT And Live | Tested | No
5 | Client Branch for Urgent Fixes | For client urgent requirement we made this branch | Deliverd | Working on UAT | Tested | No
6 | Mention Functionality on Home page Post & Announcement | Main home page | Deliverd | Working but need attention | Tested | No
7 | Credential Lock Featurs | Super admin can lock any company all employee credential | Deliverd | Working on UAT but need the toaster when user login through Microsoft | Tested | No
|  | Admin or the authorised person can lock the organization which will lock the credentials of the employees in the organization | Deliverd | working on Uat | Tested | No
|  | Admin or the authorised person can lock the credentials of any specific employee | Deliverd | Working on UAt | Tested | No
8 | Mobile App Ui | ISA Mobile App Ui Build | Deliverd | UI is done but functionality is inprogress. | 45-50% Completed | yes
|  | Profile Pic Change From Mobile App | Deliverd | Working on UAT | Tested | No
|  | Dark Theme In Emossy Mobile And Login Page Change | Deliverd | Working on UAT | Tested | No
|  | App deployment to Play store | Deliverd | Working on UAT | Tested | No
|  | Clock in reflection in web And App | Deliverd | Working on UAT | Tested | No
9 | Dashboard mention with mail | Mention employee in post and comment with mail Integration | Deliverd | Working on UAT | Tested | No
10 | All Employee | we can update Department and Designation of employee | Deliverd | Working on UAT | Tested | No
11 | Theme Header | Set Navigation bar image for Republic Day till 28 jan | Deliverd | Working on UAT | Tested | No
12 | User Access Permission | remove static role condition on Ticket Master,Me, and Assets Master and changes in the backend and frontend and flow test with user permissions | Deliverd |  | Under Testing | yes
13 | Company Website visit | Company Website visit on click of logo or name click in navigation bar | Deliverd | Working on UAT | Tested | No

## Emossy Module work
S.no | Module | Responsible
1 | Timesheet Bug | Priya / Ravi
2 | Payroll Bugs | Harshit / Bhavendra
3 | User Access Bugs | Shagun / Ankit
4 | Hiring Bugs | Shagun / Ankit
5 | Todo Bugs | Suraj / Pradanya
6 | Performance Bugs | Deepali / Mayank
7 | Home Page Bugs | Harshit / Bhavendra
8 | Intranet and Side Navigation Bugs | Shagun / Ankit
9 | Project Bugs | Priya / Ravi
10 | Helpdesk | Shagun / Ankit
11 | Organization | Harshit / Bhavendra
12 | Employee data | Harshit / Bhavendra
13 | Career , FAQ, News Header | Deepali / Mayank
14 | Figma for any New Requirement or change request | Charan
15 | Bugs finding in all modules | Shounak / Manish
16 | Urgent Bugs Fix P-1 | Suraj / Pradanya
17 | Mobile App ISA and App related issue | Faizan
18 | Shift, Week-Off, Attandance and Leave | Harshit / Bhaven
19 | EFMS Bugs | Deepali / Ankit
20 | Dashboard | Priya / Ravi
21 | ME Module | Bhavendra sir / Harshit sir
22 | Assets Master | Bhavendra sir / Harshit sir
23 | Profile | Bhavendra sir / Harshit sir

## PM Requirements
Sr.no | Requirement from PM for Reports | Requirment From | Priority | Status
Date Of Last Deployment = 03, Jan 2023
1 | Admin can view and export reports of all inactive employees who are not login there task on Time sheet or not using timesheet | AK Sir | P2 | Pending
2 | Automatically shoot mail to all non working employees of Time sheet | AK Sir | P2 | Pending
3 | Automatically shoot mail to all employees who miss there time sheet to fill with reminder along with pending days | AK Sir | P2 | Pending
4 | Export Report of who completed work on given time and not comleted on time | AK Sir | P2 | Pending
5 | Code Working Slow on Live | Himanshu Pandey | P1 | Pending
6 | Popup on Create Task – Increase the size | Himanshu Pandey | P1 | Pending
7 | Popup On Create Task – Not According To Figma | Himanshu Pandey | P2 | Pending
8 | Kan Ban – Facing Issue while changing Task in Kan Ban | Himanshu Pandey | P1 | Pending

## Colour Code Priority List
Priority | Level | Colour
RoadBlock | RoadBlock
P1 | High
P2 | Medium
P3 | Low

## Fix Project
S.No. | Bug | Bug On | Priority | Status
Date Of Last Deployment = 03, Jan 2023
1 | Project List Is Not order By Create Date i.e. New project are showing at the end of project list. | Backend | P2 | Pending
2 | UI Responsive Issue In Project Module In Laptop | Frontend | P2 | Pending
3 | Font Size Ok Kan Ban Increse | Frontend | P3 | Pending

## Fix Hiring
S.No. | Bug | Bug On | Priority | Status
Date Of Last Deployment = 03, Jan 2023
1 | Apply Condition In Hiring Like : Experience 0 then Fresher ¦ Salary = 0 then Not-Disclose. In the Carrer Portal | Frontend | P2 | Pending

## Fix Time sheet Critical
sr.no | Bug
1 | Check box log time
2 | Search Filter
3 | % update
4 | Task assignee box
5 | Pagination in timesheet page and also manage many task
6 | Project Tile description getting out from box
7 | Bug 1008 | Bhavendra sir | Payroll
8 | Bug 1009 | Bhavendra sir | Payroll
9 | Bug 1010 | Bhavendra sir | Payroll
10 | Bug 1011 | Bhavendra sir | Payroll
11 | Bug 1012 | Ravi Sir | Projects
12 | Bug 1013 | Shagun Sir | Recruitment | P1
13 | Bug 1014 | Shagun Sir | Recruitment | P1
2023-05-01
14 | Bug 1015 | Ravi Sir | Projects | P1
15 | Bug 1016 | Ravi Sir | Projects | P1
16 | Bug 1017 | Ravi Sir | Projects | P1
17 | Bug 1018 | Ankit sir | Recruitment | P1
18 | Bug 1019 | Shagun Sir | Recruitment | P1
19 | Bug 1020 | Ankit sir | Recruitment | P1
20 | Bug 1021 | Ankit sir | Recruitment | P1
21 | Bug 1022 | Ankit sir | Recruitment | P1
22 | Bug 1023 | Ankit sir | Recruitment | P1
23 | Bug 1024 | Ankit sir | Recruitment | P1
24 | Bug 1025 | Ankit sir | Recruitment | P1
25 | Bug 1026 | Ankit sir | Recruitment | P1
26 | Bug 1027 | Shagun sir | Recruitment | P1
27 | Bug 1028 | Shagun sir | Recruitment | P1
28 | Bug 1029 | Shagun sir | Recruitment | P1
29 | Bug 1030 | Shagun sir | Recruitment | P1
30 | Bug 1031 | Shagun sir | Recruitment | P1
31 | Bug 1032 | Shagun sir | Recruitment | P1
32 | Bug 1033 | Bhavendra sir | Dashboard | P1
33 | Bug 1034 | Ravi sir | Projects | P1
34 | Bug 1035 | Ravi sir | Dashboard | P1
35 | Bug 1036 | Ravi sir | Projects | P1
36 | Bug 1037 | Bhavendra sir | Dashboard | P1
37 | Bug 1038 | Bhavendra sir | Dashboard | P1
38 | Bug 1039 | Ravi sir | Projects | P1

## Pay Roll Fixes
S.No. | Bug | Bug On | Priority | Status | Done By
Date Of Last Deployment = 03, Jan 2023
1 | When We Delete Ad-Hoc Component Page will not load and deleted component show on the that page. If i Reload a Page it removed but page realocate to the comonent tab. Not get still on ad-hoc component tab. | Frontend | P2 | Pending
2 | When we add Ad-Hoc and come to add new ad-hoc component the validation message still there that not removed from the pop up box | Frontend | P2 | Pending
3 | Add a message on Add Tax Deduction Popup box so end user can understand min limit and max limit was monthly not yearly | Frontend | P2 | Pending
4 | Mat step horizontal relod issue fix after reload it will land u where u left it last time | Frontend | P2 | Complete
5 | empty sumittion while updating profile on emossyapp.emossy.com | Frontend | P1 | Complete
6 | Birthday and annivarsary suggetion by Ashiwin sir | Frontend | P3 | Complete

## Client Requirement
S.No. | Requirment | Module | Priority | Client Name | Status
Date Of Last Deployment = 03, Jan 2023
1 | Diary View / To Do List Section. | New