## Sheet1
Story Count | Story | Date | Comment | Lable
1 | Kanban board | 2023-03-01 | Drag & Drop facility with status change automatically) | P-1
2 | Add Employee with option of add others task , approved task | 2023-03-01 | Provide facility to manager that he can give power to his sub ordinate in his absence selected subordinate can create task for team , approve task or delete task also in a check box | P-1
3 | Project or Sub Project |  |  | Under Discussion
4 | one task assign to multiple employee | 2023-03-01 | Stepwise completed with add hrs | Under Discussion
5 | Mail integration when we assign a task to user | 2023-03-01 | When task created , and closed or send for approval | P-1
6 | Multiple Comment with @ Mention | 2023-03-01 | Discussion or chat window | P-1
7 | Multiple Attachment Highlighted blue link | 2023-03-01 | Link will be clickable and view attached file when user click on it | P-1
8 | Excel type (Jira, Azure, Emossy) | 2023-03-01 | Azure , Jira and Emossy selection in Import excel option in drop down | P-1
9 | All Employee List Not Visible | 21-1-2022 | Completed | done
10 | Highlight Padding Approval Tab | 2023-03-01 | Pending tab will glow or show notification dot if any approval is pending | P-1
11 | Remove Extra Comment | 21-1-2022 | Completed | done
12 | On click of dashboard task rout on project task | 2023-03-01 | All dashboard content will rout to task sheet and filtered result as per dashboard option | P-1
13 | Delete project manager | 2023-03-01 | Without Adding new PM into project old PM will not remove from project | P-1
14 | Add user stories (parent child flow) | 2023-10-01 | Task will be create under user stories in a parent and child flow | P-3
15 | Admin can view all org project and create task also | 2023-03-01 | Admin can view all project of organization also create task but delete and approval of task will not available | P-1
16 | employee can see only his task on dashboard and project task but PM can view all task of his team on both dashboard and project task | 2023-03-01 | When developer or Employee login to project he only able to view his task but manager can view all is employees task | P-1
17 | Repo Link Attachment | Next Sprint | 3 Type (Frontend, Backend, Others) | P-3
18 | Code Reviewer Add | Next Sprint | Multiple People (Angular, dot net, #C Others) | P-3
19 | Modified Dashboard | Next Sprint | Ashwin ji provided that dashboard | P-3
20 | Document upload Tab with Description Last Save date | Next Sprint | Document name , type, Dynamic (SOW, BRD,PRD, Flow Chart, Others) | P-2
21 | Setisfaction Bar In Help Desk | Next Sprint | Provide Ticket Creator a satisfaction bar to rate his issue resolved process | P-3
22 | Whole Week or Month Task | Next Sprint | If manager create task for his employees for a month or 2 week then same task will be carry forware in next week time sheet and add time in his total log time | P-1